## Sheet1
Task Number | Task Name | Description | Assigned to | Status
1 | All Possible Traffic Light Combinations | List out All Possible Traffic Light Combinations | Niladri | Done
2 | All Possible Traffic Light Combinations at a Junction(refer Task 2 Info) | List out All Possible Traffic Light Combinations at Junction(2way) | Nilesh & Vyom | Done
|  | List out All Possible Traffic Light Combinations at Junction(4way& 6 way) | Nilesh | Done
3 | Make structures (Backend) (refer to Data Structure Description) | Map Extension Node | Nilesh & Vyom | Done
|  | Traffic Signal Junction | Nilesh & Vyom | Done
|  | Street | Pranshu | Done
|  | Traffic Signal Light | Nilesh & Vyom | Done
|  | Vehicle | Nilesh & Vyom | Done
|  | Direction | Nilesh & Vyom | Done
|  | Lane | Pranshu | Done
| Graph Data Structure (Backend) (refer Graph Representation file) | Adjacent List Node | Pranshu | Done
|  | Adjacent List | Pranshu | Done
|  | Graph | Pranshu | Done
| Make Structures (Graphics - Frontend) (refer to the Graphics Description file) | Coordinate | Pranshu | Done
|  | Style | Pranshu | Done
4 | Make Functions (Backend) | Main | Pranshu | In Progress >75%
|  | Menu(s) | Pranshu | Done
|  | Create TSL | NIlesh | Done
|  | Create TSJ | NIlesh | Done
|  | Set TSL Mode | Pranshu | Done
|  | Set TSJ Mode | Pranshu | Done
|  | Create Map Extension | Nilesh | Done
|  | Map Extension Operations(Add,Delete,Edit) | Nilesh | Done
|  | Set ID | Pranshu | Done
|  | Get ID | Pranshu | Done
|  | Create Street | Nilesh | Done
|  | Create Lane | Nilesh | Done
|  | Road Queue( create, delete, insert) | Nilesh | Done
| Make Functions (Simulator) | Simulate | Nilesh & Vyom | In progress
|  | Analyze | Nilesh & Vyom | Done
|  | Get Directions | Nilesh & Vyom | In Progress
|  | Update Map Extension Nodes | Nilesh & Vyom | Done
|  | Update Vehicles | Nilesh & Vyom | Done
| Make Functions (Graphics-Frontend) | Initialize Coordinates | Niladri | Done
|  | Initialize Style | Niladri | Done
|  | Set Coordinate | Niladri | Done
|  | Set Style | Niladri | Done
|  | Draw Lane | Niladri | In Progress
|  | Draw Street | Niladri | Done
|  | Draw TSJ | Niladri | Done
|  | Draw TSL | Niladri | Done
5 | Compiling the Code - Header Files | Graph | Vyom | In Progress
|  | Map Extension Node | Vyom | In Progress
|  | Traffic Components | Vyom | In Progress
|  | Graphics | Niladri | In Progress